## #51 Nashville.Madison Closing
Closing Office
Notes from Jamie Bing 4/14/2025
1767 (1732) Gallatin Pike North, Suite 9F Madison, TN 37115
Office # | 51
On-site Location
Moving Current Office | Closing this location and looking for new space. | But looking for new Nashville office once I know about 2 pending contracts
USPS Mail changed to | Tammie changed 4.16.26 DONE | Forward to office 27 Crown Staffing 1809 East 9th St Hopkinsville KY 42240
Lease Date | Expires 4/30/26
Estimated Move Date | Jamie B Team to have everything removed by end of Lease Term. | 4/27 and 4/28 and cleaned on 4/29
Marketing to update Google | Tanner/Lindsey | Please do not shut down google page. I will alert with new address asap but won't be this month
Shred- It bins | NONE
Sign Removal and Repair | Larry follow up with Jamie B team to see when she wants it removed, but needs to be done by the end of the Lease. | I will get this handled with local contractor by the end of day 4/30
Office Cleaned Out | Jamie B Team. | will be done by contracor on 4/29
Confirm who will follow up with returning keys to the landlord | Elizabeth with the LL prop. mgr. team is able to meet on 5/1/26, at 9 am Madison timezone. | Could that be done on Friday 5/1/2026 at 9am? I can have someone meet the landlord that day as long as a scheduled time
All utilities have been set up for termination as of end of lease | Jamie B Team to set up termination of all utilities by the end of the lease term. | I will have Benita handle this scheduled for Monday 5/4/26. So that we can do walk through on 5/1 and give them chance to transfer
Trash Service? Does bin need picked up | Jamie B Team to determine and terminate | I will have Benita handle this scheduled for Monday 5/4/26. So that we can do walk through on 5/1 and give them chance to transfer
HVAC Contract in place? Does it need to be canceled? | Tammie notified Luther Jr's Heating & Cooling LLC to end the HVAC Maint. contract as of end of the lease term date. 3/4/26. Luther responded back that we never had a maintenance plan with them.
Contact Insurer to remove off of our policy at end of lease term | Tammie notified our Insurer to remove this off of our policy as of end of the lease term. Sent notification on 4/16/26. DONE
What current employees, if any, will transfer to another office? |  | Employee resigned so we are having this covered with other staff as needed now. JB
I.T. Equipment has been returned? | IT TEAM follow up with Jamie B Team
Request Deposit | Tammie has sent notice to the LL of where to send our deposit back when she sent notice not to renew 11/10/25. Tammie will follow up on Deposit $1,922.00
Update Quarem | Tammie will do.
Received Deposit | Tammie will follow up
Update Office list/Office In Full | Tammie will do when closed
Ann to updated Amazon address | Ann closer to close date. Ann was notified to close on 4/16/26. | Can be done now. No more orders going there
What needs to be done to get space in handover condition | See below for specifics or reach out to Tammie with any questions.
Notice send to the LL | Tammie sent 11/10/25
Send notice to HQ | Tammie sent 3/4/26, 4/14/26
Move out Procedures in Lease term | Lease terms on how we are to leave the space
| Broom-clean condition, in good condition and repair, except for ordinary wear and tear | Understood JB
| Remove all furnishings, equipment, trade fixtures, merchandise, signs, and other personal property at Tenant's expense | Understood JB
| Repair any damage caused by the removal of such items | Understood JB
| If required by Landlord, remove alterations, additions, and improvements made by Tenant and restore the areas to their original condition, except for Tenant's Initial Improvements, which do not need to be removed. | Understood JB

## #50 Greenville Closing
Closing Office
21 Orchard Park Drive, Suite G Greenville, SC 29615
Office # | 50
On-site Location
Moving Current Office | Closing
USPS Mail changed to | Jamie B Team, please let Tammie know where to forward mail.
Lease Date | Expires 5/31/26
Estimated Move Date | n/a
Marketing to update Google | Tanner/Lindsey closer to end of Lease term.
Shred- It bins | NONE
Sign Removal and Repair | Larry follow up with Jamie B team to see when she wants it removed, but needs to be done by the end of the Lease.
Office Cleaned Out | Jamie B Team.
Confirm who will follow up with returning keys to the landlord | Jamie B Team to let Tammie know when to coordinate with the LL.
All utilities have been set up for termination as of end of lease | Jamie B Team to set up termination of all utilities by the end of the lease term.
Trash Service? Does bin need picked up | Jamie B Team to determine and terminate
HVAC Contract in place? Does it need to be canceled? | Tammie notified Carolina Climate control no services after Lease expiration date of 5/31/26. Notified on 3/2/26. Carolina Climate will fix the thermostat wire issue sometime the week of 4/20. They will contact Tammie with date and time soon.
Contact Insurer to remove off of our policy at end of lease term | Tammie will need to do in May
What current employees, if any, will transfer to another office? | Local employees do not know of this closer please keep this info at HQ level only.
I.T. Equipment has been returned? | IT TEAM follow up with Jamie B Team
Request Deposit | There is no deposit on file in Quarem for this location.
Update Quarem | Tammie will do in May
Received Deposit | n/a
Update Office list/Office In Full | Tammie will do when closed
Ann to updated Amazon address | Ann closer to close date.
What needs to be done to get space in handover condition | See below
Notice send to the LL | Tammie sent 1/13/26
Send notice to HQ | Tammie notified HQ managers. 3/4/26, 4/14/26
Move out Procedures in Lease term | Lease terms on how we are to leave the space
1 | Same Condition as at the Beginning of the Lease: The premises must be delivered to the landlord in the same condition as at the beginning of the lease, except for ordinary wear and tear and damages caused by fire or casualty. | Brooke Fry acknowledged receiving the notice we would not be renewing. She said the prop mgr would be in contact closer to end of lease for walkthru and key return. 1/20/26
2 | Removal of Improvements: All improvements made by the tenant during the lease term will become the property of the landlord. However, the landlord may direct the tenant to remove any improvements or additions deemed undesirable, and the tenant must comply and repair any damage caused by the removal.
3 | Signage Removal: The tenant must remove all signage, including fascia signs and other tenant identification signage, and repair any holes or damage caused by the removal.
4 | Broom Clean Condition: The premises must be left in a "broom clean" leasable condition.
HVAC Systems: The HVAC systems must be in good working order, allowing for normal wear and tear.
5 | Keys: All storefront and mailbox keys (if applicable) must be returned to the landlord.
6 | Free of Liens and Violations: The premises must be surrendered free and clear of all liens, charges, or encumbrances resulting from the tenant's actions or omissions, and clear of any violations placed by federal, state, or municipal authorities.
7
8

## #49 Columbus HCCombine 2024-202
Closing/Combining Office
572 Metro Place North Dublin, OH 43017
Office # | #49, Combining with office #03
On-site Location
Moving Current Office | Closing office location & Combining with #03
USPS Mail changed to
Lease Date | 8/1/21 to 8/1/26 (staff moving to 5300 West Pointe Plaza Columbus, OH 43026, on 8/26/24). Looking to sublease.
Estimated Move Date | Staff move 8/26/24, Items moved to HQ 8/20/24, Jayna removed some items on 8/21/24, Jayna to come back week of 8/26/24, to move some more items to other office locations. DR site will remain at #49, until subleased.
Marketing to update Google | Marketing
Shred- It bins | Cancelled and picked up on 8/21/24
Sign Removal and Repair | Larry will address the Monument sign. Tammie will have MRS remove all the decals in all the windows.
Office Cleaned Out | Staff move 8/26/24, Items moved to HQ 8/20/24, Jayna removed some items on 8/21/24, Jayna to come back week of 8/26/24, to move some more items to other office locations. DR site will remain at #49, until subleased.
Confirm local person who will follow up with returning keys to the landlord | Tammie will handle.
All utilities have been set up for termination as of end of lease | Tammie will shut off closer to end of lease.
Trash Service? Does bin need picked up | ---
HVAC Contract in place? Does it need to be canceled? | New system. Quarterly Maintenance change filters
Contact Insurer to remove off of our policy at end of lease term | Contact once a new tenant has been found.
What current employees, if any, will transfer to the new location? | Madeline Sanders will be moving to #03, on 8/26/24
I.T. Equipment has been returned? Contact Ben Liu | I.T. removed 2-TV's, Alexa on 8/20/24, Jayna removed (2) I-9 Stations and is taking them to Dayton, She took (2) phones, (2) Keyboards, (5) monitors on 8/21/24, remaining items will be removed in future. DR site will remain at this office until end of lease or until a Sublessor has been found. Jay wants us to check into current locations in Cinci or Northern KY to move the DR site to.
Request Deposit | No security deposit on file in Quarem.
Update Quarem | Tammie will update at the end of the term.
Received Deposit | NA
Remove off of our Ins. Policy | Tammie will notify our insurer towards the end of our lease.
Update Office list/Office In Full | Done 8/22/24
Ann to updated Amazon address | Notified Ann on 8/22/24
DR Site | Looking into other options of where to relocate the DR Site by the end of this lease.

## #16 Clarksville, IN Temp Closed
Closing Office
1240 Veterans Parkway Ste 200, Clarksville, IN 47129
Office # | 16
On-site Location
Moving Current Office | Temp Closed Per Ryan 3/26/26 (LL is looking for a possible new tenant)
USPS Mail changed to | Tammie sent email to Ryan if he wants the mail changed 3/26/26. He wants it changed to Dixie office.
Lease Date | 2027-03-31
Estimated Move Date | n/a
Marketing to update Google | Lindsey spoke with Ryans team on 3/25/26, regarding this
Shred- It bins | NONE
Sign Removal and Repair | Larry follow up with Ryans team once a new tenant has been identified or closer to end of the lease term.
Office Cleaned Out | Ryan team once a new tenant has been identified or closer to end of the lease term.
Confirm who will follow up with returning keys to the landlord | Ryan team once a new tenant has been identified or closer to end of the lease term.
All utilities have been set up for termination as of end of lease | Ryan team to set up termination of all utilities by the end of the lease term.
Trash Service? Does bin need picked up | Ryan team once a new tenant has been identified or closer to end of the lease term.
HVAC Contract in place? Does it need to be canceled? | Still in place because we are still in lease. Tammie will reach out to Ryan to allow the contractor access when needed. 3/26/26
Contact Insurer to remove off of our policy at end of lease term | Tammie will need to do when we are out of lease terms.
What current employees, if any, will transfer to another office? | ?
I.T. Equipment has been returned? | IT TEAM follow up with Ryan
Request Deposit | Depends on if we finish this lease or get out early ($2,186.67)
Update Quarem | Tammie will do when we are out of the lease
Received Deposit
Update Office list/Office In Full | Tammie updated temp closed per Ryan as of 3/25/26, when he confirmed with Lindsey it was not currently staffed or open.
Ann to updated Amazon address | Ann closer to close date. Ryan said if there is no charge keep it open until we are out of the lease in case he staffs this location at a later date. 3/26/26
What needs to be done to get space in handover condition | See below
Notice send to the LL | Tammie mailed LL asking if we could do a buyout Nov/Dec 2025, but LL said no and that they would only consider if a new tenant was found.
Send notice to HQ | Sent email to HQ 3/26/26
Move out Procedures in Lease term | Lease terms on how we are to leave the space
1
2
3
4
5
6
7
8

## #16 Poplar Temp Closed
Closing Office
3795 Poplar Level Road Louisville, KY 40213
Office # | 16
On-site Location
Moving Current Office | Temp Closed Per Ryan 3/26/26
USPS Mail changed to | Tammie sent email to Ryan if he wants the mail changed 3/26/26. Change address to Dixie per Ryan 3/27
Lease Date | 2028-11-30
Estimated Move Date | n/a
Marketing to update Google | Lindsey spoke with Ryans team on 3/26/26, regarding this
Shred- It bins | NONE
Sign Removal and Repair | Larry follow up with Ryans team closer to end of the lease term.
Office Cleaned Out | Ryan team closer to end of the lease term.
Confirm who will follow up with returning keys to the landlord | Ryan team closer to end of the lease term.
All utilities have been set up for termination as of end of lease | Ryan team to set up termination of all utilities by the end of the lease term.
Trash Service? Does bin need picked up | Ryan team closer to end of the lease term.
HVAC Contract in place? Does it need to be canceled? | Still in place because we are still in lease. Tammie will reach out to Ryan to allow the contractor access when needed. 3/26/26
Contact Insurer to remove off of our policy at end of lease term | Tammie will need to do when we are out of lease terms.
What current employees, if any, will transfer to another office? | ?
I.T. Equipment has been returned? | IT TEAM follow up with Ryan
Request Deposit | 3284.88
Update Quarem | Tammie will do when we are out of the lease
Received Deposit
Update Office list/Office In Full | Tammie updated temp closed per Ryan as of 3/26/26
Ann to updated Amazon address | Ann closer to close date. Ryan said if there is no charge keep it open until we are out of the lease in case he staffs this location at a later date. 3/26/26
What needs to be done to get space in handover condition | See below
Notice send to the LL
Send notice to HQ
Move out Procedures in Lease term | Lease terms on how we are to leave the space
1
2
3
4
5
6
7
8

## #21 Aurora Closed 42525. Open u
Closing Office
1244 N Lake Street Aurora, IL 60506
Office # | #21
On-site Location
Current Office | No, Perm. closed as of 4/25/25. Projected to open back up 3/30/26. OPEN AN OPERATING!
USPS Mail changed to | Burbank location for USPS and overnights to Joliet, Per Tiffany. Tammie sent email and will change with USPS. 4/25/25
Lease Date | Expires 8/31/27
Estimated Move Date
Marketing to update Google | Tanner confirmed he will update on 4/25/25, closed. Larry mentioned the marketing will update all internet and website listings the weekend of 3/13/26, and it will be live on 3/16/26.
Shred- It bins | Gina sent cancellation notice to shred-it on 4/25/25, Gina has been notified to coordinate with Shred-it and Tiff/Matt on shred-it picking up the final bins.
Sign Removal and Repair | Larry has been notifed. 4/25/25. Opening back up so not removing sign at this time. 3/12/26
Office Cleaned Out
Tammie to confirm what needs to be done to space to secure deposit & return keys to LL
All utilities have been set up for termination as of end of lease
Trash Service? Does bin need picked up
HVAC Contract in place? Does it need to be canceled?
Contact Insurer to remove off of our policy at end of lease term | tbd, this cannot be done until we are out of the lease
What current employees, if any, will transfer to the new location?
I.T. Equipment | Melissa E. said appt scheduled on 3/10/26 to have network equipment installed. Following that, the internet connection and remaining equipment installation will be completed shortly after.
Request Deposit | deposit $2,046.85
Update Quarem
Received Deposit
Remove off of our Ins. Policy
Update Office list/Office In Full | Tammie updated 4/25/25
Ann to updated Amazon address | Ann, was notified 4/25/25, and confirmed change same day. Tammie notified Ann to update the Amazon account. 3/12/26
Water cooler rented | Matt is canceling this service and setting up w/vendor pickup 4/29/25
Shannon and Melissa to update | Shannon and Melissa confirmed open and operating 3/31/26.
Business License 2026 | Tracee K. applied for new business license. Waiting on that before we occupy the office again. 3/10/26. Per Melissa the business license has been obtained 3/12/26

## #65 Lawrenceburg Move DONE
Moving office
13918 Wilson Creek Rd Aurora, IN 47001
Office # | 65
On-site Location
Moving Current Office | 878 W Eads Pkwy Lawrenceburg, IN 47025
USPS Mail changed to | Tammie changed 8/28/25
Lease Date | Expires 8/31/25
Estimated Move Date | 2025-08-30
Tanner/Lindsey to update Google | Notify Tanner and Lindsey to update as soon as we have confirmation of new address.
Shred- It bins | N/A
Sign Removal and Repair | Larry has set up to be removed 8/29/25, Tammie is tranporting the sign to Miamisburg the same day.
Office Cleaned Out | Chelsea is handling this 8/30/25
Confirm who will follow up with returning keys to the landlord | Chelsea is scheduled to do the final walkthrough with tech at 11 am on 8/30/25
All utilities have been set up for termination as of end of lease | Chelsea will schedule on 8/29/25. Chelsea is to email Amy from Regency to let her know it has been completed before 3 pm.
Trash Service? Does bin need picked up | Chelsea, to cancel with Rumpke. 9/4/25.
HVAC Contract in place? Does it need to be canceled? | Forwarded the last inspection and final inspection to the Prop mgr. 8/25/25. Also, cancelled services with the vendor.
Contact Insurer to remove off of our policy at end of lease term | Tammie notifed insurer to remove off our policy as of 9/1/25
What current employees, if any, will transfer to another office? | ??
I.T. Equipment has been returned? | Chelsea will move to new location
Request Deposit | Deposit in amount of $1,200
Update Quarem | Done
Received Deposit | received ck3252, on 10/16/25, 1200
Update Office list/Office In Full | Tammie completed on 8/28/25
Ann to updated Amazon address | Tammie notified Ann to change for 8/29/25
What needs to be done to get space in handover condition | Prop mgr sent list on items
Notice send to the LL | Tammie notified LL.
Per Prop Mgr to do list below:
1. Chelsea, Remove all personal property.
2. Larry, Remove facade signage, pylon signage if we have it, repair and paint. Chelsea or Larry, Remove all wall and window decals.
3. Tammie, HVAC last inspection and a final inspection due to submitted. Done 8/25/25
4. Chelsea, Shall deliver in broom clean condition.
5. Chelsea, Move out inspection to be scheduled with Amy.
6. Chelsea, Any issues found during inspection that is tenants responsibility must be resolved by tenant within (10) days.
7. Once the Premises is deemed acceptable by LL, LL shall provide a confirmation of acceptance.
8. LL shall provide a current statement of Tenant's account within (20) days.
9. If the Lease requires reconciliation of common area maintenance, real estate taxes and/or insurance, the reconciliation shall be provided after the year end calculates are completed for the Shopping Center. Tenant’s account will be charged or credited for any difference after the reconciliation adjustment. If Tenant’s account is charged, Tenant shall pay Landlord promptly any amounts due and payable. If Tenant’s account is a credit, Landlord shall refund Tenant by check within twenty (20) days after the reconciliation adjustment. Should you have any questions during this surrender period, please contact me.

## #65 Lawrenceburg DONE
New Office Questionnaire
878 W Eads Pkwy Lawrenceburg, IN 47025
Office # | 65
On-site Location
Moving Current Office | 13918 Wilson Creek Rd Aurora, IN 47001
New Office Street Address | 878 W Eads Pkwy
Suite #
City, State Zip | Lawrenceburg, IN 47025
Lease Date | Chelsea sharing space with current tenant for month of September. Lease official possession date is 10/1/25, with a rent commencement date of 11/1/25
Estimated Opening Date | Official 10/1/25
Please indicate below which programs you will need new accounts for and who should have logins:
Facebook (list editors) | Tammie sent message to Tanner, Lindsey and Chelsea to coordianate 9/25/25
Indeed
Sense
Careerbuilder
Zip Recruiter
Website Listing
Google Business Pages
Please answer the following questions…. | Please type your answer below
Have you confirmed the internet speed available is at least 100/10mps? | Diego has Comcast to be transferred and be effective as of 9/28/25
Are you already providing service to a client in the new area?
What current employees, if any, will transfer to the new location? | ??
Will you be hiring any new staff for this location? | ??
Do you need a new phone number? If so, please list the AREA CODE and PREFIX you prefer. | This is a move
Will you want a fax number? | This is a move
Will you be doing any construction before moving in? | Chelsea plans to have the counter removed, flooring installed and the space painted. LL is giving rent abatement for the month of October.
Are there datalines already run? If so, how many per workstation? (Should at least be 2) | Chelsea to coordinate with IT
Will you need a landing page added to the website? | ??
Do you need HVAC Maintenance Contract per Lease? | Clarks will do this location. They used to service our previous location as well.
Do you need a Pest Control Contract per Lease? | n/a
Do you anticipate doing any healthcare business?
Please send a floorplan of the office to Tammie Hoffer and Tech Support. | Chelsea to provide.
Please connect with Larry Shuman to discuss signage. | Sign supposed to be installed on 11/4/25
Sign approval from landlord and city permit? | LL has approved overhead sign on building and also approved 2 pylon signs to be placed under the T-mobile signs
Utilities have been turned on at this location? | Chelsea plans to share space with current tenant for the month of Sept. Chelsea will need to have utilites turned on into our name after this.
Emergency Evacuation Plans in Place? Fire Extinguisher in office at time of opening?
Mailing Address Change | Completed 8/28/25
Update Office in Full and Office Sites list | Completed 8/28/25
Send out email to HQ | Tammie sent out on 9/25/25
Business License Update | Tracee completed
Amazon address update. | Tammie notified Ann to complete on 8/29/25
Notify HR if New State in beginning stage | n/a
Notify OP'S if New State in beginning stage | n/a
Notify Op's 1-wk prior to office opening if same state
Cert. of Occup. | Tammie paid for new tenant application permit on 9/25/25. Per John Johnson in zoing approved same day.
Add to Insurance Policy (property) | Tammie sent to insurer to add effective 10/1/25, on 9/23/25

## #21 Palatine 2025 DONE
Closing Office
448 E. Dundee Road Palatine, IL 60074
Office # | 21
On-site Location
Moving Current Office | Moving everything to Villa Park location.
USPS Mail changed to | Tammie changed 8/12/25
Lease Date | Expires 9/30/2025
Estimated Move Date | Moved 8/20-8/23
Tanner/Lindsey to update Google | Notified Tanner and Lindsey to update Google as of 8/20/25, Palatine will be closed as of this date. | 18th
Shred- It bins | Shred it bins picked up 8/20/25. DONE | #3000159768, on website next service date is 10/3/25.
Sign Removal and Repair | LL will have his maintenance person flip the sign around for $100 or less.
Office Cleaned Out | Items scheduled to be moved 8/20-8/23. MRS and Tammie cleaned out.
Confirm who will follow up with returning keys to the landlord | Tammie left the keys with staf at Villa Park. LL will go by and pick the keys up form there. 8/22/25
All utilities have been set up for termination as of end of lease | See below.
Trash Service? Does bin need picked up | Tammie called Groot and they said they would call back the aurthorized user ont he acct to confirm a cancellation. They said they would call back between 24 to 48 hrs from 8/25/25. | grout
HVAC Contract in place? Does it need to be canceled? | No HVAC Contract
Contact Insurer to remove off of our policy at end of lease term | Tammie sent email to broker to remove off of our policy effective 9/1/25
What current employees, if any, will transfer to another office? | ??
I.T. Equipment has been returned? | Tammie returned some equipment to HQ and all other was moved to Villa.
Request Deposit | Received deposit $505.00 11/3/25. LL deducted for common area, 2024 & 2025 real estate, reverse of sign insert.
Update Quarem | Tammie will do.
Received Deposit | Received deposit $505.00 11/3/25. LL deducted for common area, 2024 & 2025 real estate, reverse of sign insert.
Update Office list/Office In Full | Tammie updated 8/12/25
Ann to updated Amazon address | Tammie notified Ann to cancel by 8/20
What needs to be done to get space in handover condition | Done.
Notice send to the LL | Tammie notified LL.
Utilities that need to be canceled. Tammie will reach out to each vendor except for Comcast.
| 1. Nicor Gas, Account 46-07-02-18717, meter 4952130, 1-888-642-6748 | 448 E Dundee Rd | Spoke to Morgan and both accts will stop service as of 8/26/25. Confir # 2044284192
| 2.Nicor Gas, Account 08-82-25-29718, meter 4767615 | 446 E Dundee Rd | Spoke to Morgan and both accts will stop service as of 8/26/25. Confir # 2044284192
| 3. Comed Electric, Account 2153825000 | 446 E Dundee Rd | Spoke to Daniel and both accts will stop service as of 8/26/25. Confir. will be sent to email chicago.aurora
| 4. Comed Electric, Account 9776435000 | 448 E Dundee Rd | Spoke to Daniel and both accts will stop service as of 8/26/25. Confir. will be sent to email chicago.aurora
| 5. Village of Palatine Water/Sewer, Account 510531103-002 | 448 E Dundee Rd | Spoke to Vicki and both accts will stop service as of 8/25/25. Final bill will be sent out as of 8/29/25
| 6. Village of Palatine Water/Sewer, Account 510531003-002 | 446 E Dundee Rd | Spoke to Vicki and both accts will stop service as of 8/25/25. Final bill will be sent out as of 8/29/25
| 7. Groot, Inc, Waste, Account 3092-416704 |  | Called spoke to a rep. she said that the commercial sales dept has to call our listed authorized user back to confirm the cancellation. 8/25/25 She said to give them 24 to 48 hours to call back. Relaying message to Melissa. 8/25/25
8. Comcast, sent to IT to cancel

## #57 JaxClose DONE
Closing Office
3832 Baymeadows Rd, Suite 7, Jacksonville, FL 32217
Office # | 57
On-site Location
Moving Current Office | Closed
USPS Mail changed to | Tammie changed 6/23/25 to HQ
Lease Date | Expires 2/14/26
Estimated Move Date | Final walkthrough was 7/28/25, by Tammie DONE!
Lindsey/Tanner to update Google | Tanner to follow up with Tiff/Matt. 6/23/25
Shred- It bins | None
Sign Removal and Repair | Channel letter sign removed, disposed of, patched and painted on 7/8/25. Decals removed on 7/25/25.
Office Cleaned Out | Done 7/28/25
Confirm local person who will follow up with returning keys to the landlord | Tammie to do a final walkthrough with LL rep on 7/28/25 @ 9am. Early lease term to be sent after LL agrees space is being turned over in acceptable condition and LL will be returning deposit. Tammie will have accounting send final buyout after LL agrees acceptable.
All utilities have been set up for termination as of end of lease | Shawn sent email to JEA customerservice@jea.com requesting for services to be disconnected on 7/31/25. Tammie will follow up with Shawn to make sure he received a confirmation email. Shawn sent email on 7/24/25. LL confirmed it was transferred back into their name on 7/30/25. DONE.
Trash Service? Does bin need picked up | n/a
HVAC Contract in place? Does it need to be canceled? | Gina has been notified to cancel this HVAC maint. contract 7/3/25. Per Gina this is done.
Contact Insurer to remove off of our policy at end of lease term | Tammie contacted new broker to remove this off of our policy as of 7/30/25.
What current employees, if any, will transfer to the new location? | Tiff will notify current employees 6/20
I.T. Equipment has been returned? Contact Ben H. | Ben said that Tiff returned what was needed to be returned the end of June.
Request Deposit | Deposit of $2,831.04 (LL will return deposit if all items are removed including graphics and signs). Deducted from buyout cost.
Update Quarem | Archived as of 7/30/25
Received Deposit | Received 7/28/25, we owed for a buyout $18,014.58, LL sent this "Instead of you paying the $18,014.58 and then I send you the $2,831.04 security deposit, you can just pay the net $15,183.54 please."
Update Office list/Office In Full | Done 6/23/25, Tammie
Ann to updated Amazon address | Tammie notified Ann to update on 6/19/25
Send out HQ Email notifying of new Address | Tammie will notify HQ on 6/23
Tammie sent email to LL asking if there is an early option to term. lease prior to 2/14/26. Sent email 6/23/25

## #39 DyerClose 2024 DONE
Closing Office
910 Richard Road, Suite B Dyer, IN 46311
Office # | 39 (used to be 68, but combined with 39)
On-site Location
Moving Current Office | Not moving just closing.
USPS Mail changed to | Changed as of 7/16/24, effective beginning 7/23/24 online th
Lease Date | 5/1/23 to 4/30/25 (office staff last day 7/26/24)
Estimated Move Date | Office staff last day is 7/26/24, LL is going to relist this office for lease and let us know if and when he finds a new lessor.
Tanner to update Google | 7/26/24, Remind Tanner to update
Shred- It bins | LL confirmed the bin(s) were removed on 8/2/24. Done
Sign Removal and Repair | Richard called me and said he will remove our sign plate and put it in our office. It is our responsibility to get it from there. He will put up his for rent sign in place. It should cost less than $200 to do this. 7/16/24 He will do it after 7/26/24, I let Larry know by person on 7/16/24. I talked to the LL on 8/26/24, and he said he has shown our space several times to date. He said that he has placed for rent signs in the windows of the space. He has someone that will take our sign down and he will put a for rent sign up when that happens. He said we will need to coordinate getting our sign and we have 1 mat left in the space. He will let me know when the sign is down. He will also let me know when he has found a new tenant. I will follow up again with him in a few weeks if I have not heard back. 8/26/24, Also there is a 4 drawer filing cabinet we need to remove as well when we coordinate for the other items to be removed. 8/27/24, per LL. Everything has been removed per Melissa E. 9/6/24.
Office Cleaned Out | Computers are being moved Per Melissa 7/26/24, Desks per Paul he is going to reach out to company we bought them from and see if they may want to buy them back. If not, he will let me know if I should ask LL if they may want to buy them. 7/12/24. Done on 7/26/24. Keys were left at office by Melissa 9/6/24
Confirm local person who will follow up with returning keys to the landlord | Melissa E. did this on 7/26/24
All utilities have been set up for termination as of end of lease | LL confirmed he called for the final readings on the utilities on 8/2/24.
Trash Service? Does bin need picked up | LL handles the trash per Melissa E. 7/16/24
HVAC Contract in place? Does it need to be canceled? | Nothing per Melissa E. 7/16/24
Contact Insurer to remove off of our policy at end of lease term | Sent to remove off our our policy on 12/30/24
What current employees, if any, will transfer to the new location? | Employee is leaving company. 7/26/24
I.T. Equipment has been returned? Contact Ben Liu | I called Comcast Business and cancelled the Dyer office's internet today 7/17/2024 (with Melissa's permission), and the cancellation fee is: $245 plus 30 days of service fee (Comcast required 30 days notification of their services). I also changed the billing address to our Burbank office, so we won't miss the final bill. IT will send someone to Dyer office Friday, July 26, 2024 to pickup all the networking equipment and any computer equipment you don't need. Please let me know if you have any questions or concerns. Per Ben L
Request Deposit | $1,500 deposit (unknown if the LL will keep since we are breaking lease early waiting to hear back). Deposit to go towards flooring repair cost (10K).
Update Quarem | Heather to archive in Quarem.
Received Deposit | See above
Remove off of our Ins. Policy | Sent to remove off our our policy on 12/30/24
Update Office list/Office In Full | Need to remove as of 7/26/24
Ann to updated Amazon address | Notified Ann on 7/16/24 last day 7/26/24
Richard LL cell 219-384-3510
Email from the LL on 8/2/24.
Tammie,
The Shred-it people removed their equipment.
I have called for final readings on the utilities.
As of now, the large sign has not been removed.
I have shown the unit to a couple of people with connections to the market.
I’ll let you know more asap.
Early Termination to Lease effective 12/30/24. LL billed 10k for flooring repair. LL kept deposit of 1500 and accounting to send LL on or before 1/10/25, the remaining 8,500. DONE!

## #02 MainvilleClose 2024 DONE
Closing Office
3187 Western Row Rd, Suite 107 Mainville, OH 45039
Office # | 2
On-site Location | 3187 Western Row Rd, Ste 107 Mainville, OH 45039
Moving Current Office | Not looking for a new space at this time. Just closing this location.
USPS Mail changed to | Tammie changed to forward to Springdale location 11.6.24
Lease Date | Expires 11/30/24
Estimated Move Date | Kendra will have everything out by the last week of November.
Tanner/Lindsey to update Google | Tanner to update on 11/25
Shred- It bins | Shred it bin(s) picked up on 11/18/24, when regular empty of bin(s) were completed. Kendra confirmed. 11/18/24
Sign Removal and Repair | Vendor preparing quote for removal between 10/14-17. Tammie has reached out to get the exterior paint color for patches/paint if needed. th 9/20 & 9/23. Larry has this set up to be removed and repaired with Atlantic Sign Company. Sign was removed on 11/1/24
Office Cleaned Out | Kendra will have everything out by the last week of November.
Confirm local person who will follow up with returning keys to the landlord | Kendra is scheduled to meet with Property Manager Denny on 11/27. Kendra sent pictures of unit right before walk through with Denny. 11/26/27
All utilities have been set up for termination as of end of lease | Kendra will be handling this.
Trash Service? Does bin need picked up | Kendra will handle if needed.
HVAC Contract in place? Does it need to be canceled? | Per Jayna no HVAC contract in place. 10/31/24
Contact Insurer to remove off of our policy at end of lease term | Tammie sent to insurer change form on 11/5/24
What current employees, if any, will transfer to another office? | ??
I.T. Equipment has been returned? | Diego is scheduled to remove IT equipment on 11/25
Request Deposit | Tammie 1200. LL kept deposit deducting from carpet cleaning, sheetrock repairs.
Update Quarem | Heather to do
Received Deposit | Tammie will follow up on this. LL deducted we did not get this back.
Update Office list/Office In Full | Tammie Completed 11/25/24
Larry Rytell accepted notification we are not renewing this location. Denny Moore will be our contact for the close of the property (Property Manager)
Ann to updated Amazon address | Ann confirmed on 11/25/24, she removed from our Amazon acct.
Water Heater broke over weekend 11/8/24, Kendra will have it repaired and let me know when that has been done. She notified me on 11/12, there was an issue. th Vendor working on this 11/25/24

## #05 Indy.Plainfield DONE
Closing Office
148 N. Perry Rd Plainfield, IN 46168
Office # | #05
On-site Location
Moving Current Office | This office is temporary being moved to Greenwood until a new office location is identified. Plainfield office location closing due to LL term lease early. (Moving staff to Greenwood location 7781 South U.S. 31 Indianapolis, IN 46227)
USPS Mail changed to | Tammie changed for 11/11/24, to 7781 South U.S. 31 Indianapolis, IN 46227 (Greenwood)
Lease Date | 3/31/26 (LEASE TERM ENDING EARLY PER LL 2-weeks). LL notified us on 11/5/24
Estimated Move Date | By 11/11/24
Tanner/Lindsey to update Google | Tanner to update on 11/7/24
Shred- It bins | Tammie will contact shred it. Ryan will have shred it bin moved to Greenwood. Tammie will cancel for Plainfield and set up service for Greenwood. Waiting on shred it to get this on their schedule. Holly reached out to get this scheduled, but Candice said the bin(s) were not taken to Greenwood. I followed up with Ryan to see if they were taken to storage and then I can see how to get this scheduled. 11/18/24. These were picked up from our Greenwood location per Candice.
Sign Removal and Repair | Scheduled to be completed on 11/7, per Larry
Office Cleaned Out | Ryan has scheduled movers.
Confirm local person who will follow up with returning keys to the landlord | Candice is to meet with Camden to return the keys on 11/13/24
All utilities have been set up for termination as of end of lease | Candice gave this info to the LL (Josh) so he can get these switched to their name. 11/12/24. LL confirmed they will transfer as of 11/14/24 CenterPoint Energy Acct 13286579-1, Edge Utilies Acct 295960, Duke Energy Acct 9101 1989 9841 Candice cancelled Spectrum 11/12/24.
Trash Service? Does bin need picked up | Candice said this is a shared dumpster no trash service to cancel. 11/5/24
HVAC Contract in place? Does it need to be canceled? | Have Gina check to see if we have HVAC service plan if so she needs to cancel this is writing with the vendor. Gina is to cancel services with Rinehart Heating & Cooling, Inc. 11/5/24. Gina received email confirmation from Kim at Rinehart that they acknowledge the cancellation. 11/5/24
Contact Insurer to remove off of our policy at end of lease term | Tammie has scheduled with our insurer to have removed off of our policy as of 11/20/24
What current employees, if any, will transfer to another office? | 3-coordinators at this location. Ryan will have them move to Greenwood.
I.T. Equipment has been returned? | Ben H. to go to Indy and meet with Ryan either this week or next week. (11/5 to 11/11) - Ryan said an IT person is not needed in person - Ben H. Fortinet equipment is being sent back by Ryan. - Ben H
Request Deposit | Per LL they are ending our lease early and we will not get our deposit back. 11/5/24
Update Quarem | Tammie to update Quarem so no more rent payments are scheduled to be made. Kristina placed the vendor on hold so no more rent payments are scheduled to be made. 11/5/24
Received Deposit | LL is not returning
Update Office list/Office In Full | Tammie updated 11/6/24
Ann to updated Amazon address | Ann updated 11/7/24
Overnights | Payroll/Accounting please start sending overnights to Greenwood location as of 11/11/24. Tracee confirmed they will start sending these as of 11/11/24, to Greenwood location. 11/5/24
Window Cleaning? | Candice left voicemail to cancel Fish Window Cleaning 11/12/24
Water Cooler/Water Service? | Candice will call to cancel water delivery and have them pick up the coolers for the closed offices this one and 86th
Pest Control? | Candice cancelled Pest Control 11/12/24

## #05, Indy.86th St. DONE
Closing Office
1299A W. 86th St. Indianapolis, IN 46260
Office # | #05
On-site Location
Moving Current Office | Office is Temp. Closed. Permanently Closing by 12/31/24
USPS Mail changed to | Completed 12/9
Lease Date | Orig. Lease date 12/31/25, Early Termination by 12/31/24
Estimated Move Date | Final walkthrough was completed by Tammie with Tracey Creal on 12/9/24
Tanner/Lindsey to update Google | All location pages, Google, Apple, and the Website will be down by 12/5
Shred- It bins | Shred it bins were removed on 11/13/24, Candice confirmed.
Sign Removal and Repair | Sign deconstruction and patching scheduled for 12/5
Office Cleaned Out | Candice will do a spot clean after movers are done.
Confirm local person who will follow up with returning keys to the landlord | Tammie did final walk through with Tracey Creal on 12/9
All utilities have been set up for termination as of end of lease | Meter Numbers: AES Meter # 1237651 Citizens #212604189 for water Citizens #732403 for gas
Trash Service? Does bin need picked up | Use building dumpster, no need to have bin picked up.
HVAC Contract in place? Does it need to be canceled? | Gina notified HVAC company. 11/20
Contact Insurer to remove off of our policy at end of lease term | Effective 12/9/24, contacted insurer to remove when I got the signed lease back from LL on 12/19/24
What current employees, if any, will transfer to another office? | ??
I.T. Equipment has been returned? | Ben H. to coordinate with Candice/Ryan. Candice will turn the internet off closer to end of early termination date 12/31/24. Equipment is being sent back to HQ per Ryan -Ben H Tammie brought back a box of stuff from Indy and gave to Ann in IT 12/9
Request Deposit | 2309.97 | Deposit will be held by LL until Recon for CAM due no later than 3/31/25
Update Quarem
Received Deposit
Update Office list/Office In Full | Done 12/19/24
Ann to updated Amazon address | Ann updated 12/19
Overnights | Tracee K. to check with Candice/Ryan
Window Cleaning? | Not at this location
Water Cooler/Water Service? | Have cooler there, have cancelled all deliveries. I'll schedule to have cooler picked up. Candice
Pest Control? | Services have been cancelled. Candice
Ceiling Needs Repaired | completed in December
Accounts Payable | Kristina made last payment for Dec. 2024, and she has placed this vendor on hold. 11/25/24
HVAC system should have been replaced by the LL, but they decided to wait until the Spring to do it per the Property Manager Tracey.

## #50 CurrentOld SpartanburgMove
Closing Office Space move to new future location
100 North Town Dr, Unit 7 Spartanburg, OH 29303
Office # | 50
On-site Location
Moving Current Office | Moving to 246 E. Blackstock Rd, Ste "i" Spartanburg, SC 29301
USPS Mail changed to | 2024-08-12
Lease Date | Expires 12/31/24, Per Jamie B. do not pay rent for the last 3-months due to roofing issues. Accounting has been notified.. Jamie B is to mail the keys to the property manager Terri M. 9/30/24 | th 9/23/24, acct notified
Estimated Move Date | 2024-08-01
Tanner/Lindsey to update Google | Sent email out 8/9/24
Shred- It bins | None at this location
Sign Removal and Repair | Need to find out from Jamie B when she wants this sign to come down. Larry to follow up with Jamie B. 9/23/24
Office Cleaned Out | Per Jamie B it will be cleaned out by 9/30/24.
Confirm local person who will follow up with returning keys to the landlord | Tammie will reach out to the PM and ask if they want the keys to be mailed back to them or if they want to meet Jamie B on the 30th to get the keys. 9/23/24 Jamie B is mailing keys to the property manager 9/30/24
All utilities have been set up for termination as of end of lease | Benita to handle turning off the utilities by 9/30/24
Trash Service? Does bin need picked up | If there is trash service Benita will handle termination as of 9/30/24
HVAC Contract in place? Does it need to be canceled? | N/A
Contact Insurer to remove off of our policy at end of lease term | I explained to the insurer we are not paying last 3 months rent per Jamie B, we are handing keys over as of 9/30/24, and our lease doesn't expire until 12/31/24. Asked them if we should keep on our policy until 12/31/24? Notified Insurer to remove off of the policy as of 12/31/14
What current employees, if any, will transfer to the new location? | They have moved already. Moved in August 2024
I.T. Equipment has been returned? Contact Ben Liu | Internet to be shut off 8/12/24, per Ben
Request Deposit | Need to request $1,293.00 (may not get back since we are not paying last 3 months rent)
Update Quarem | Tammie to do when lease ends.
Received Deposit | Tammie to follow up on deposit of 1,293 (may not get back since we are not paying last 3 months rent)
Update Office list/Office In Full | Done 8/9/24
This office has outstanding issues with roof cave in and damage that occurred at beginning of July. Per Property Manager this issue has been fixed, but it is our responsibility to fix the interior. I have sent email to Jamie B. to see where she is on this and what else she needs for me to do on my end. th Sept. 2024. Per Jamie B and Jay we are not paying last 3 months lease and she wants to turn the keys over as of 9/30/24. Accounting has been notified to not pay anymore rents or CAMS after 9/30/24.
LL sending demand letters for last three months rent. Jamie B is aware. 12/19/24

## #14 North VernonCurrent SpaceMo
Closing Office Space move to new future location
1200 West O & M Avenue Room 206, North Vernon, IN 47265
Office # | 14
On-site Location
Moving Current Office | Neg. space at 35 South State Street, Unit 5 North Vernon, IN 47265
USPS Mail changed to | Tammie completed. Changed for 10/31
Lease Date | Expires 4/30/25, but local staff has been notified that the LL will allow us out of our lease early. New agreed on end of term as of 10/31/24.
Estimated Move Date | Week of 10/28 to 11/1 (Tammie to meet PM on 10/28/24, to do walk thru and get keys. Tammie will drop keys off at the current location same day), Per Rebecca Date of move is 10/31
Lindsey/Tanner to update Google | Lindsey to update 10/31/24
Shred- It bins | n/a
Sign Removal and Repair | Per Larry no sign to remove. 9/24/24
Office Cleaned Out | Kim and Eva will be packing up and cleaning this office. Move scheduled for the 31st . DONE Handed over keys. 10/31/24
Confirm local person who will follow up with returning keys to the landlord | Rebecca to organize (Kim or Eva)
All utilities have been set up for termination as of end of lease | Gross lease utilities are paid by the LL. Confirm this with Rebecca
Trash Service? Does bin need picked up | N/A
HVAC Contract in place? Does it need to be canceled? | N/A
Contact Insurer to remove off of our policy at end of lease term | Tammie completed form to add new space and remove this space to insurer on 10/9/24
What current employees, if any, will transfer to the new location? | Kim and Eva
I.T. Equipment has been returned? Contact Ben H. | Ben H notified as of 9/24/24, and again on 10/7/24, Ben H to organize move with Rebecca Bishop
Request Deposit | N/A
Update Quarem | Tammie completed 10/9/24
Received Deposit | N/A
Update Office list/Office In Full | Tammie updated 10/29/24
Ann to updated Amazon address | Tammie notified Ann 10/244/24
Send out HQ Email notifying of new Address | Tammie to notify HQ by 10/31/24
Business License/Permit/Cert. Of Occup. (Is there one for this space and should it be transferred for new space) | Tammie completed the business license permit and submitted it, inspection scheduled for 10/11 at 9am, Rebecca paid the $50 fee to city on 10/10/24, Tammie will follow up on making sure we passed the inspection on 10/14/24, for new space. Marie city contact said we did not have a business license permit on file for this location?
Notes from Jayna when looking for new space.
This building was bought so the owner is really lenient on the details but for a timeline I would say November.
Open layout we have two ladies that occupy that space.
We could have offices in this new space but it's not necessary.
Let's shoot for a 3 year lease if possible.
Angi Tungate
to me, Jayna, Kimberly, Evangelina, Rebecca
Kim - Is the Workone center still wanting space with us? That would be a benefit for us. NO GO FOR SHARING A SPACE WITH WORKONE
Angi Tungate¦Business Development Manager
Northern KY
Southern IN
859-445-7494
www.crownstaffing.com
Kimberly Wright
to Angi, me, Jayna, Evangelina, Rebecca
Yes, they said if we found a space we could share they would be interested.
LL has told Rebecca we can get out of the lease early if we want to. 9/19/24. Rebecca asked her to call me because she hasn't returned my phone calls. th
Reaching out to negotiate space at 35 South State Street, Unit 5, North Vernon, IN 47265, th 9/18/24, 9/19/24
New LL as of 10/1/24, per Mayor we have to start sending rent payments to Annalee Alexander 812-767-1342, imaginationdaycareandpreschool@yahoo.com, I have left several messages and also sending a follow up email as of 9/23/24

## #14 North VernonNew Space 2024.
Moving office to this new location
35 S State Street, Ste 5, North Vernon, IN 47282
Office # | 14
On-site Location
Moving Current Office | 1200 West O&M Ave Room 206 North Vernon, IN 47265
New Office Street Address | 35 South State Street
Suite # | Unit 5
City, State Zip | North Vernon, IN 47282
Lease Date | 11/1/24 to 10/31/25, possession 10/28/24
Estimated Opening Date | 2024-11-01
Please indicate below which programs you will need new accounts for and who should have logins:
Facebook (list editors) | Lindsey/Tanner ?
Indeed
Sense
Careerbuilder
Zip Recruiter
Website Listing
Google Business Pages
Please answer the following questions…. | Please type your answer below
Have you confirmed the internet speed available is at least 100/10mps? | Ben H said internet is good. Sept. 2024, Sent message to Ben H. about getting with Jayna and Rebecca about coordinating IT to get Internet turned on, phones moved the week of 10/28, Tammie. Internet is scheduled to be turned on 10/31. Internet will be shut-off at old location on 10/31. Aaron will be travelling to assist with move on 10/31 -Ben
Are you already providing service to a client in the new area?
What current employees, if any, will transfer to the new location? | Kim and Eva
Will you be hiring any new staff for this location? | Per Rebecca no new staff needed.
Do you need a new phone number? If so, please list the AREA CODE and PREFIX you prefer. | No new number needed
Will you want a fax number? | This is a move.
Will you be doing any construction before moving in? | No, per Jayna/Rebecca. Tammie has submitted for the business license permit, inspection scheduled for 10/11 at 9am. Rebecca pd $50 fee on 10/10/24 . Marie Shepherd was not answering me back so I left several messages and finally reached Suzy who stated the inspector did not pass this location because there were several electrical outlets not working. She said the inspector notified the property owner. I reached out to Ashlee Morris the property manager who said she will check in on this. Suzy or Marie is susposed to reach out to me and let me know the status after speaking to the inspector again. 10/22/24. Business permit issued and Rebecca to pick up. Also, copy emailed to Tammie.
Are there datalines already run? If so, how many per workstation? (Should at least be 2) | IT to verify
Will you need a landing page added to the website? | Per Rebecca, no
Do you need HVAC Maintenance Contract per Lease? | No, gross lease maintenance is LL responsibility.
Do you need a Pest Control Contract per Lease? | No, gross lease maintenance is LL responsibility.
Do you anticipate doing any healthcare business? | Per Rebecca not at this time.
Please send a floorplan of the office to Tammie Hoffer and Tech Support. | Tammie completed on 10/28/24
Please connect with Larry Shuman to discuss signage. | Larry will need to reach out to the Property Manager, Ashlee Morris 812-366-2288, Larry notified 10/9/24. Larry is working with a vendor and has Ashlee's approval as of 11/6/24
Sign approval from landlord and city permit? | Ashlee approved as of 11/6/24
Utilities have been turned on at this location? | This is a gross lease. Not needed. LL pays
Emergency Evacuation Plans in Place? Fire Extinguisher in office at time of opening? | Rebecca/Jayna ??
Mailing Address Change | Tammie completed. Changed for 10/31
Update Office in Full and Office Sites list | Tammie updated 10/29/24
Send out email to HQ | Tammie sent out email on 10/29/24
Business License Update | Tracee, Tammie applied for the Business Permit Application on 9/30/24 (online-email Marie Shepherd), They will send the inspector out and send us an email for the invoice. Waiting on Proptery Manager and LL to get an electrician out to correct what the inspector noted on the inspection. Once this is completed the county will issue the business permit. 10/22/24, TH Business Permit was issued.
Amazon address update. | Tammie notified Ann 10/22/24
Notify HR if New State in beginning stage | na
Notify OP'S if New State in beginning stage | na
Notify Op's 1-wk prior to office opening if same state | Sent email 10/22/24

## #57 JacksonvilleNew Office 2024
New Office Questionnaire
8713 Old Kings Rd S., Jacksonville, FL 32217
Office # | 57
On-site Location
Moving Current Office | 3832 Baymeadows Rd, Suite 7, Jacksonville, FL 32217
New Office Street Address | JAY DECIDED FOR US TO RENEW. Renewed for 1-yr.
Suite #
City, State Zip
Lease Date
Estimated Opening Date
Please indicate below which programs you will need new accounts for and who should have logins:
Facebook (list editors)
Indeed
Sense
Careerbuilder
Zip Recruiter
Website Listing
Google Business Pages
Please answer the following questions…. | Please type your answer below
Have you confirmed the internet speed available is at least 100/10mps?
Are you already providing service to a client in the new area?
What current employees, if any, will transfer to the new location?
Will you be hiring any new staff for this location?
Do you need a new phone number? If so, please list the AREA CODE and PREFIX you prefer. | This is a move
Will you want a fax number? | This is a move
Will you be doing any construction before moving in?
Are there datalines already run? If so, how many per workstation? (Should at least be 2)
Will you need a landing page added to the website?
Do you need HVAC Maintenance Contract per Lease?
Do you need a Pest Control Contract per Lease?
Do you anticipate doing any healthcare business?
Please send a floorplan of the office to Tammie Hoffer and Tech Support.
Please connect with Larry Shuman to discuss signage.
Sign approval from landlord and city permit?
Utilities have been turned on at this location?
Emergency Evacuation Plans in Place? Fire Extinguisher in office at time of opening?
Mailing Address Change
Update Office in Full and Office Sites list
Send out email to HQ
Business License Update
Amazon address update.
Notify HR if New State in beginning stage
Notify OP'S if New State in beginning stage
Notify Op's 1-wk prior to office opening if same state

## #50 New SpartanburgDONE! 2024
New Office Questionnaire
246 E. Blackstock Rd., Ste "i" Spartanburg, SC 29301 - Jamie Bing
Office # | 50
On-site Location
Moving Current Office | 100 North Town Dr, Unit 7 Spartanburg, SC 29303 (exp. 12/31/24)
New Office Street Address | 246 E. Blackstock Rd.
Suite # | "i"
City, State Zip | Spartanburg, SC 29301
Lease Date | 2024-04-08
Estimated Opening Date | Officially open 8/12/24. Sent out notice to HQ on 8/9/24, th
Please indicate below which programs you will need new accounts for and who should have logins:
Facebook (list editors) | Get with Tanner to update Google by 8/12, Sent out notice.
Indeed
Sense
Careerbuilder
Zip Recruiter
Website Listing
Google Business Pages
Please answer the following questions…. | Please type your answer below
Have you confirmed the internet speed available is at least 100/10mps? | Ben team to start set up internet 8/6, equipment 8/8 & 8/9,
Are you already providing service to a client in the new area? | Yes, previous location being moved. th
What current employees, if any, will transfer to the new location? | Employees are in this office as of August 2024
Will you be hiring any new staff for this location?
Do you need a new phone number? If so, please list the AREA CODE and PREFIX you prefer. | This is a move, so no new phone number needed. BL
Will you want a fax number? | We already have a fax number for Spartanburg office, and it's: 864-754-3677
Will you be doing any construction before moving in? | Paint/ replace some ceiling tiles. Jamie B will have Tim complete this work.
Are there datalines already run? If so, how many per workstation? (Should at least be 2) | ??
Will you need a landing page added to the website? | ??
Do you need HVAC Maintenance Contract per Lease? | Yes, in place with Davis Services, Inc. 1-yr contract in place 4/15/24 to 4/15/25, emailed contract to Jamie B. th 1st service needs set up once this office is up and running. reached out to Jamie B and Benita they would like for HQ to handle the scheduling and services. Tammie notified Gina to get this on the schedule for 1st service and remainder of services. 8/9/24
Do you need a Pest Control Contract per Lease? | Jamie B. asked Tammie to put this in place once we are in the new location I can get this set up for regular maintenance. Asked Gina to get estimates and get Jamie B to approve one and get this set up. 8/9/24. Done Gina to follow.
Do you anticipate doing any healthcare business?
Please send a floorplan of the office to Tammie Hoffer and Tech Support. | Jamie B. said she will do a sketch for the Emergency Evacuation plan
Please connect with Larry Shuman to discuss signage. | Larry is working with sign vendor. 4/23/24, th Sign was completed and installed as of 6/11/24, per Larry Per Jamie B. Larry is ordering window, door, wall decals and deliver to Hopkinsville by 8/2
Sign approval from landlord and city permit? | Sign approved by landlord. 4/18/24, th
Utilities have been turned on at this location? | Per Jamie B. utilities are in Crown's name May 2024
Emergency Evacuation Plans in Place? Fire Extinguisher in office at time of opening? | Jamie B. said she will do a sketch for the Emergency Evacuation plan
Mailing Address Change | Tammie updated Address as of 7/23/24, for effective date of 8/12
Update Office in Full and Office Sites list | Done 8/9/24
Send out email to HQ | Done 8/9/24
Business License Update | Tracee said all she needs to do is update the business license address once we have moved. Remind her to do this as of 8/12/24. Sent email to Tracee and Victor to do this on 8/9/24
Amazon address update. | Ann Marks has been notified to update by 8/12. She confirmed receipt
Notify HR if New State in beginning stage
Notify OP'S if New State in beginning stage
Notify Op's 1-wk prior to office opening if same state

## #61 New Birmingham.BessemerDONE
Closing Office Space move to new future location
5031 Ford Parkway, Ste 110-111 Bessemer, AL 35022
Office # | 61, 64
On-site Location
Moving Current Office | Moving from 700 Academy Dr Ste 116 Bessemer, AL 35022
USPS Mail changed to | Gina will go to the post office and fill out form to forward mail to 1819 E 9th Street Hopkinsville, KY 42240, Gina was able to complete online 7/2/24
Lease Date | 7/1/24 to 6/30/27, two renewal options for additional 3-yr term with 60-day notice.
Estimated Move Date | 7/22, estimated move in date. business license updated, corkey putting in a new unit, 1 works 1 does not, Tim has painted, carpet, cat 6 ines almost done, graphics today, and furniture being put together today by Tims team (7/11/24) Cert of Occup. is not required per City of Bessemer unless we are making structural/electrical/plumbing. All we need is a Updated Business License which Victor set up and sent over on 7/11/24. Up and running July 2024. DONE
Tanner to update Google | Let Tanner know he can update once I have confirmation on moving date.
Shred- It bins | Need to request for the shred it bins to be updated for pick up at this new address. Benita is going to get me the barcodes for this change. 7/1/24, I sent email to Holly on 7/1/24. Holly confirmed email on 7/2/24. Holly said as of 8/1/24, the new pickups will be to the new location. I will need to follow up and verify this happens. 1st pick up scheduled for 8/2/24 at the new location.
Sign install | Larry working on this. 7/1/24
Office Move and Set up | Jamie B to organize per conversation 7/1/24
Who will get keys from LL | Corkey dropped off keys to our current Bessemer location to Alex. 7/1/24
All utilities have been set up | Benita is handling setting up utilities. 7/1/24. She is supposed to let me know so I can get the LL out to inspect all systems and to check the exit light signs. Corkey did inspections and is replacing 1 of the 2 HVAC units. 7/11/24 per Jamie B
Trash Service? Does bin need picked up | This is included in our gross rent
HVAC Contract in place? Does it need to be canceled? | Will need a HVAC contract put into place for this location. On schedule to get quotes starting 7/15/24, th Gina is working on this. Per Gina "Brown" is the vendor for HVAC Benita is handling pest control. 8/27/24
Pest Control Contract | Benita said she put a pest control contract in place for this location because it needed it. It is not required per lease.
Contact Insurer to remove off of our policy at end of lease term | sent request to insurer to remove this location as of 7/31/24, and to add the new location as of 7/1/24. snt 7/1/24
What current employees, if any, will transfer to the new location? | Alexandria Brown
I.T. Equipment has been returned? Contact Ben Liu | Per Jamie B. Ben's team will be down on the 12th. Make sure Ben shuts of internet for the old office the end of the month.
Send Deposit | No deposit for this location.
Update Quarem | updated 7/2/24
Received Deposit | 0
Add to our insurance policy | sent to be added on 7/1/24
Update Office list/Office In Full | Done
Need w-9 and new vendor set up | Requested from corkey then send to mckenzie and then i can set up in quarem. 7/1/24
Business License | Sent email to Tracee and Victor to check if our current business license will work for this location or do we need a new one. 7/2/24. Victor changed address to reflect new location for the business license. 7/11/24. Saved a copy. Per Victor they did not say we needed any inspections.
Exit Lights and Fire Ext. | LL is to ck the exit lights and verify they are working. Alexandria Brown is going to get the 2 fire ext. on the 11th and drop them off to the new office to Tim (Contractor)
Updated GP | Kelly Gonce confirmed she updated in GP on 7/17/24
Cert of Occup. | Tammie has called left several messages and sent several emails trying to get the application process details. No one has returned any of my messages to date 7/3/24 Cert of Occup. not needed per City of Bessemer. See above just need update our business license. 7/11/24

## #36 Union CentreMove DONE! 2024
Closing Office Space move to new future location
5653 Union Centre Drive West Chester, OH 45069
Office # | 36
On-site Location | 5653 Union Centre Dr. West Chester, OH 45069
Moving Current Office | Still looking for a space
USPS Mail changed to | Springdale location as of 5/28/24
Lease Date | 6/1/17 to 5/31/24
Estimated Move Date | 5/28/24, Per Kendra
Tanner to update Google | List the location as moved to the Springdale, per Marcus 5/28/24
Shred- It bins | Shred it has not picked up yet as requested so Kendra moved to mainville. Tammie reached out to Holly to have them picked up at the mainville location (2 bins)
Sign Removal and Repair | Done, per Larry
Office Cleaned Out | Done per Kendra 5/28/24
Confirm local person who will follow up with returning keys to the landlord | Kendra to do on the 31st at 10 am . Done 5/31/24
All utilities have been set up for termination as of end of lease | Kendra to do. Kendra forwarded info stating the acct. 02-0108411 for Rumpke Service has been stopped and billing will be stopped.
Trash Service? Does bin need picked up | n/a
HVAC Contract in place? Does it need to be canceled? | Kendra reached out to Willis One Hours to stop HVAC service at this location. She said they told her they have made a note on our file and a rep would call her back to cancel. She will keep me updated. 5/31/24
Contact Insurer to remove off of our policy at end of lease term | Tammie to do
What current employees, if any, will transfer to the new location? | Kendra
I.T. Equipment has been returned? Contact Ben Liu | IT will be there on Friday, May 31, 2024 to help Marcus team to remove all IT equipment (to the office that Marcus wants to storage)
Request Deposit | $562.50, requested to be sent back in notice letter, th rcvd deposit minus CAM charges 7/23/24 DONE! | notified LL will be deducting 2023, CAM reconcillations from our deposit 7/16/24 | Please see below for JE and note:
Update Quarem | Tammie to do
Received Deposit | Tammie will follow up on this |  | 382.66 1004-8-0-0 LB
Remove off of our Ins. Policy | Sent request to insurer as of 5/28/24, th |  | 179.84 6100-36-14-0 Rent Exp Union Ctr
Update Office list/Office In Full | Updated working out of Springdale 5/29/24 |  | 562.50 1400-36-0-0 Rent Deposit Union Ctr
Security deposit for Union Centre lease. Lease expired 5/31/2024. Final expenses for lease in the amount of 179.84 were deducted from the deposit

## #61 BirminghamMoveDONE! 2024
Closing Office Space move to new future location
700 Academy Dr Suite 16, Bessemer, AL 35022
Office # | 61, 64
On-site Location
Moving Current Office | Moving to 5031 Ford Parkway, Ste 110-111 Bessemer, AL 35022
USPS Mail changed to | Gina, changed this online on 7/2/24, change dated effective 7/9/24
Lease Date | 8/1/24 to 7/31/24
Estimated Move Date | 7/16/24, is move date, in future Benita is going to schedule for a ribbon cutting once Larry has the signs up. Possibly in fall.
Tanner to update Google | Tanner to update google 7/16/24
Shred- It bins | Need to request for the shred it bins to be updated for pick up at this new address. Sent to Holly and she had it updated in her System.
Sign Removal and Repair | Sent Larry the pylon sign availability. Jamie B was going to check and see if we could move signs around to get two spaces side by side. Larry to follow up on this with Jamie B. 7/15/24
Office Cleaned Out | Jamie B is scheduling to get the office cleaned out. per email 7/15/24. Final walkthru scheduled for 7/25/24 at 11 am our time 10 am AL
Confirm local person who will follow up with returning keys to the landlord | I need to reach out to LL and get the final walk through scheduled for 7/24 or 7/25/24. Let Jamie B know when it is. Final walk through was completed on 7/25/24, with PM Kristi Oyster. handed over the keys and she said it looks great. We are done! No deposit to collect.
All utilities have been set up for termination as of end of lease | Benita will be handling all the termination per Jamie B 7/1/24
Trash Service? Does bin need picked up | Benita will be handling all the termination per Jamie B 7/1/24
HVAC Contract in place? Does it need to be canceled? | Benita will be handling all the termination per Jamie B 7/1/24
Contact Insurer to remove off of our policy at end of lease term | sent request to insurer to remove this location as of 7/31/24, and to add the new location as of 7/1/24. snt 7/1/24
What current employees, if any, will transfer to the new location? | Alexandria Brown
I.T. Equipment has been returned? Contact Ben Liu | IT was there week of 7/8/24, to get everything hooked up at the new location and Ben is scheduling for internet to be shut off at old location for 7/18
Request Deposit | 0 deposit in Quarem.
Update Quarem | Done
Received Deposit | 0
Remove off of our Ins. Policy | Sent request to insurer see above
Update Office list/Office In Full | Tammie done 7/15/24
Ann to updated Amazon address | 7/15/24, Tammie sent Ann email.

## #66, SomersetClose DONE 2024
Closing Office Space moved to On-Site
3311 South Highway 27, Suite 7, Somerset, KY 42503 - Ryan Atwell
Office # | 66
On-site Location | 2441 S Hwy 27, Somerset, KY 42501
Moving Current Office | Moved to on-site
USPS Mail changed to | HQ in March 2024- mail is supposed to go to Tammie to be scanned and forwarded to Jeremy Keen in Lexington
Lease Date | 5/1/23 to 4/30/24
Estimated Move Date | End of March moved to on-site. Lease ends 4/30/24
Tanner to update Google | Update google to on-site. Tanner confirmed done. March
Shred- It bins | 2-picked up end of March
Sign Removal and Repair | Larry confirmed completed in March
Office Cleaned Out | Clean up is scheduled for 4/11/24
Confirm local person who will follow up with returning keys to the landlord | Cathy Colyer will do so after office clean up
All utilities have been set up for termination as of end of lease | Katie Voss was setting up utitlity shut off for 4/30/24
Trash Service? Does bin need picked up | n/a
HVAC Contract in place? Does it need to be canceled? | n/a
Contact Insurer to remove off of our policy at end of lease term | Done 4/10/24, Tammie
What current employees, if any, will transfer to the new location? | Cathy Colyer is On-Site
I.T. Equipment has been returned? Contact Ben Liu | IT picked up all the equipment on 3/11/2024
Request Deposit | No deposit
Update Quarem | Tammie to do
Received Deposit | No deposit
Key return | Cathy to meet with the landlord